## Sheet1
Annexure - 3
Project Implementation Schedule of Transmission System
Name of Project :- 220 KV D/C Charor-Banala Line
| 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015 | [11 empty] | 2014
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
(Design & Engineerimg )
Finalisation of BOQ.Technical specification
Preperation of Bid Documents & approval of ADB
NIT & Tender Processing & agreement
Preparation of profile
Perparation of forest case
Joint inspection by Range Officer
Clearance form Patwari, SDM & DM
Submission to nodal officer
Clearance form MOEF Delhi
Final approval.
Submission of Compensation amount
Lease grant & agreement
Execution. Trans. Line
(a) Route
Final Survey & Soil /Foundation Classification & Tower Schedule
Approvals
(b) Tower
Manufacturing, Testing, Inspection
Despatch Instruction
Receipt at Site
Foundation Casting
Tower Erection
(c ) Conductor & Insulator
Manufacturing, Testing, Inspection
Despatch Instruction
Receipt at Site
Stringing
(d) Final clearances Testing & Commissioning
NOTE : √ ACTIVITY COMPLETED
`